Schedule for Consideration of

Swami Hotels Chapter 100

| Date | Event |
| --- | --- |
| September 4, 2015 | Company provides completed Chapter 100 Questionnaire information and signed engagement letter |
| September 11, 2015 | Gilmore & Bell distributes drafts of Chapter 100 Plan and Cost-Benefit Analysis |
| September 18, 2015 | City staff and Company provide comments to Chapter 100 Plan and Cost-Benefit Analysis |
| September 25, 2015 | Mail Chapter 100 notices to taxing districts along with Chapter 100 Plan and Cost-Benefit Analysis |
| October 7, 2015 | Finalize all documents for October 15 City Council meeting and deliver to City staff: - Ordinance approving Chapter 100 Plan and Cost-Benefit Analysis - Chapter 100 Plan and Cost-Benefit Analysis |
| October 8, 2015 | 4-day Sunshine Law notice of October 15 City Council meeting (§ 67.2725, RSMo) |
| October 15, 2015 | City Council meeting – Consider ordinance approving Chapter 100 Plan and Cost-Benefit Analysis |
| October 21, 2015 | Gilmore & Bell distributes draft of Performance Agreement and Chapter 100 Bond Documents |
| October 26, 2015 | City staff and Company provide comments on Performance Agreement and Chapter 100 Bond Documents |
| October 28, 2015 | Finalize all documents for November 5 City Council meeting and deliver to City staff: - Ordinance approving Performance Agreement and Chapter 100 Bond Documents - Performance Agreement - Bond Documents |
| October 29, 2015 | 4-day Sunshine Law notice of November 5 City Council meeting (§ 67.2725, RSMo) |
| November 5, 2015 | City Council meeting – Consider ordinance approving Performance Agreement and Chapter 100 Bond Documents |
| November 20, 2015 or earlier | Closing of Chapter 100 transaction |